## Goals-Objectives
Healthier Community Partnership
Significant Health Need: Community Education, Literacy and Involvement
Implementation Plan |  |  | From CHNA Research |  |  | From Community Asset Inventory
Goal | Objective | Actions | Identified Community Needs | Populations at Risk | Disparities & Root Causes | Existing Community Assets | Potential Partners
Increase Community Health Literacy | Increase Community Knowledge of Available Resources | Form community health coalition | The community identifed community education, literacy and involvement as the number one significant health need as well as a relationship between health outcomes and affluence. Those with the lowest income and education generally have the poorest health outcomes. | Those who didn't graduate high school, lower income families, | Lack of trust in the health industry. | Meals on Wheels, Pregnancy Care Center, Southside & Pampa Senior Citizens Centers, Schools, Churches, PRMC, Community and Youth Center, Chamber of Commerce, EDC, Altrusa, Lions, Optimist, Kiwanis Clubs, Good Samaritan, United Way, and other Non Profits, Parks, Fitness Centers, Trails, Extension. | Meals on Wheels, Pregnancy Care Center, Southside & Pampa Senior Citizens Centers, Schools, Churches, PRMC, Community and Youth Center, Chamber of Commerce, EDC, Altrusa, Lions, Optimist, Kiwanis Clubs, Good Samaritan, United Way, and other Non Profits, Parks, Fitness Centers, Trails, Extension, City of Pampa, Gray County.
|  | Inventory health and education efforts and resources | County health rankings suggest Gray County has a higher rate of smokers, teen births, percentage of uninsured, preventable hospitals stays and a lower percentage of mammography screenings. |  | Lack of health literacy- unsure of insurance issues, unlikely to take health condition serioulsy and are not compliant.
Coorindate health and education efforts and resources as well as engage social media.
| Educate the community on medicare benefits | Identify medicare experts in the community. | Preventable hospital stays in Gray County were 5,644 per 100,000 Medicare enrollees which was higher than TX (4,793) and the US (4,236). | 65 and older and their families. | Some do not understand how to get the most of their Medicare benefits. |  | Meals on Wheels, Senior Centers, Extension, Chamber of Commerce, Service Clubs,
Hold educational sessions free to the community.
Significant Health Need: Access to Care
Implementation Plan |  |  | From CHNA Research |  |  | From Community Asset Inventory
Goal | Objective | Actions | Identified Community Needs | Populations at Risk | Disparities & Root Causes | Existing Community Assets | Potential Partners
Improve Access to Primary Care. | Communicate Van Availability | Increase awareness of the van by posting the number to schedule at the front desks. | The focus groups identified issues with access to care including: transportation, affordablity and non-insured. | All, Low Income. | Mobility/Transportation: Fear of falling or being a burden. |  | Churches
| Add Physicians to Primary Care Team. | Promote the community to draw physicians and their family to Gray County. |  | All |  |  | Chamber of Commerce, EDC, City of Pampa, Gray County
PRMC continue recruiting.
Significant Health Need: Community Education, Literacy and Involvement
Implementation Plan |  |  | From CHNA Research |  |  | From Community Asset Inventory
Goal | Objective | Actions | Identified Community Needs | Populations at Risk | Disparities & Root Causes | Existing Community Assets | Potential Partners
To Improve the Health of the Community Through Education. | Decrease Adult Obesity Rate (36%) by 3% in 3 Years. | Create community educational materials from local organizations to inform the community of the rate locally and the dangers of obesity. | The community identifed healthy weight as the number three significant health need. | All, particularly lower income and less educated. | Fear and misunderstanding about how to get healthy. | Meals on Wheels, Pregnancy Care Center, Southside & Pampa Senior Citizens Centers, Schools, Churches, PRMC, Community and Youth Center, Chamber of Commerce, EDC, Altrusa, Lions, Optimist, Kiwanis Clubs, Good Samaritan, United Way, and other Non Profits, Parks, Fitness Centers, Trails, Extension. | Meals on Wheels, Pregnancy Care Center, Southside & Pampa Senior Citizens Centers, Schools, Churches, PRMC, Community and Youth Center, Chamber of Commerce, EDC, Altrusa, Lions, Optimist, Kiwanis Clubs, Good Samaritan, United Way, and other Non Profits, Parks, Fitness Centers, Trails, Extension.
|  | Events that highlite healthy eating and active living and promote change. | Adult obesity in Gray County was 36% higher than Tx at 31% and the US at 30%. The obesity trend has been increasing in Gray County.

## Anticipated Impact
Gray County Community Health Improvement Plan
Significant Health Need: Community education, literacy and involvement
Goal: Increase community health literacy
Objective | Actions | Target Populations | Anticipated Impact | Short-term and Long-term Outcome Measures | Collaborators | Resources Needed | Responsible Individual(s) | Timeline
Increase Community Knowledge of Available Resources | Form Community Health Coalition | All | Further the reach of the impact of the program by involving key players from the community. | Promote the programs and make them sustainable by not straining one organization. | Ministry, Volunteer Groups, Extension Service, Local Media, Senior Centers, Schools, Clubs, City, County | Colaboration to form list | PRMC | 2022
| Inventory Health and Education Efforts and Resources | All | Identify already existing programs and gaps. | To build on the foundation this creates. |  |  | Health Coalition | 2022-
| Coordinate Health and Education Efforts and Resources | All | Identify best use of resources. | Serve the community as a a community. |  |  | Health Coalition | 2022-
| Engage through social media and local media as well as support health related events. | All | Further the interaction and education of the community. | Deliver timely resources and education to a wide audience. |  | Education materials and social content | Health Coalition | 2022-
Educate the community on Medicare beneftis | Identify Medicare experts in the community | 60 plus | Identify best use of resources. | Teach the community to maximize their medicare benefits to keep them healthy. | Ministry, Volunteer Groups, Extension Service, Local Media, Senior Centers, Schools, Clubs, City, County | Education material. | Health Coalition | Late 2022-
| Hold Education Sessions free to the community. | 60 plus | Educate those on medicare and prepare others to plan before they have active medicare benefits. |  |  |  | PRMC | Late 2022-
Significant Health Need: Access to care
Goal: Improve access to primary care
Objective | Actions | Target Populations | Anticipated Impact | Short-term and Long-term Outcome Measures | Collaborators | Resources Needed | Responsible Individual(s) | Timeline
Increase physical access to care. | Communicate van availability. | At risk. | Fewer missed appointments | Increased appointments for this population |  |  |  | 2022-
| Add physicians to primary care and specialty teams | All |  |  | City, County, Chamber, EDC, DBA | Promotion of the community to draw phycisians and their family. |  | 2022-
Create Transparent Billing | Communicate charges to the patient prior to delivery of services when possible. | All | Less fear of surprise buildling | More likely to seek care. | PRMC |  | PRMC | 2023
| Promotion of programs such as MDSave, Care Credit, Etc. | Uninsured/ High Deductible Patients.. |  |  |  |  | PRMC | 2022-
Significant Health Need: Healthy weight
Goal: Improve healthy eating and active living
Objective | Actions | Target Populations | Anticipated Impact | Short-term and Long-term Outcome Measures | Collaborators | Resources Needed | Responsible Individual(s) | Timeline
Decrease obesity rate by 3% in 3 years. | Inform community of the rate locally, the dangers of obesity, etc. | All | To decrease obesity in our area by 3% in 3 years. | Healthy community, Less Risk. | Healthcare facilities, businesses, schools, media, city, county, Events such as Pampa Fest, Clubs and Organizations. | Social Content, Education Materials. | PRMC, Health Coalition | Late 2022-
| Promote change through events/education by sponsoring races and other physical activity. | All